## Findings
ID | Audit (type and date) | Date raised | Clause / control | Finding as written | Grade (major / minor / observation) | Agreed facts | Cause analysis | Correction (the instance) | Corrective action (the cause) | Owner (role) | Due | Evidence of closure | Verification date | Verifier (role) | Status
F-001 | Stage 2 initial certification, 2026-03-10 | 2026-03-12 | 9.2.2 | EXAMPLE - delete. The organisation could not demonstrate that the internal audit programme covered every applicable control across the certification cycle. | Major | The programme covered clauses 4 to 10 in the current year. Three applicable controls had no audit recorded in any year of the cycle. | The programme was rebuilt annually from the previous year rather than planned across the whole cycle, so coverage was never checked cycle-wide. | The three uncovered controls were audited and reported before the response deadline. | The programme is now planned per cycle, with a coverage matrix reviewed at each management review. | Management system owner | 2026-05-11 | Cycle audit programme v3; coverage matrix; three audit reports | 2026-05-20 | Certification body reviewer | Closed - verified
F-002 | Surveillance audit, 2027-02-08 | 2027-02-09 | 7.5.3 | EXAMPLE - delete. Two procedures presented during the audit carried no approver and no version, so the current version could not be identified. | Minor | Both documents were in use. The document control register held entries for neither. | New procedures were published from a shared folder without passing through the document control step, which sat outside the publication route. | Both procedures were versioned, approved and registered. | Publication now requires a register entry before a document can be released; the release checklist enforces it. | Owner of the document control process | 2027-04-09 | Register extract; both approved documents; revised release checklist | 2027-04-22 | Certification body reviewer | Closed - plan accepted
F-003 | Surveillance audit, 2027-02-08 | 2027-02-09 | 10.2 | EXAMPLE - delete. An opportunity for improvement: finding records close on the correction alone, with the cause field left blank in most entries. | Observation | Eleven of fourteen closed entries in the previous period carried no cause analysis. | The register had no mandatory cause field, so closure was possible without one. | Not applicable; no nonconformity was raised. | The tracker now blocks closure until cause, corrective action and a verification date are present. | Management system owner | 2027-05-08 | Tracker configuration note; sample of five reopened entries |  |  | Open - action in progress

## Read first
Findings-to-closure tracker
Version 1.0, 2026-09-05
Licence: CC BY 4.0 - reuse and adapt with attribution to GRCIDE.
Template page: https://grcide.com/templates/findings-to-closure-tracker
Companion playbook: https://grcide.com/playbooks/running-the-external-audit
Before the first audit
1. Delete the three example rows on the Findings sheet. They show the shape of a row and nothing else.
2. Fill columns A to G during the audit, from the finding as the auditor wrote it and from the evidence request log.
3. Fill columns H to P after the audit, and never close a row with columns M, N and O empty.
On grading
Grading belongs to the certification body, not to the auditee, and the tracker records it rather than arguing it. A major nonconformity affects the capability of the management system to achieve the intended results; a minor does not; several minors against one requirement can be classified as major. The practical consequence sits in the closure columns. A minor needs a plan for correction and corrective action that the body reviews and accepts. A major needs the correction and corrective action reviewed, accepted and verified before a certification decision can be taken. Split the Due column by grade accordingly, and treat a major's date as the date implementation is complete rather than the date a plan is sent. An observation is neither: record it, decide whether to act, and do not let it occupy the same queue as a nonconformity.
Two rules the columns enforce
A. Correction and corrective action are different columns because they are different acts. Correction deals with the detected instance; corrective action removes the cause so the instance does not recur. A row that fills only the correction column has not closed anything.
B. Closure is a fact, not a claim. Evidence of closure, a verification date and a named verifying role are filled together or the status stays open.
What this file does not contain
No personal data, no organisation names, no macros and no external links other than the two grcide.com pages above. The example rows are invented to show the format and describe no real audit, organisation or finding.
This template is method material published by an independent publication. It is not legal advice and does not describe any specific organisation.
Standards and certification names are the property of their respective owners. GRCIDE is an independent publication and is not affiliated with, authorized, sponsored or endorsed by ISO, IEC, NIST or any other standards body.