## Read first
One-page security strategy — version 1.0, 2026-09-05
Licence: CC BY 4.0. Reuse and adapt with attribution to GRCIDE.
What this is. One page a board or executive committee can approve. The Strategy sheet is the page: five to seven security objectives, each tied to a business objective and to a risk, each with a measure, a baseline, a target and an owner role. The Initiatives sheet holds the work that closes the gap. The Constraints sheet holds the dated obligations the plan must clear. The Review log records approvals and reviews across the horizon.
How to fill it. Delete the example rows first; every one of them is invented and prefixed EXAMPLE - delete. Start from the business objectives and the obligations register, not from a control list. Take the exposure themes from the risks sitting beyond appetite. Write each objective as an end condition rather than a project, and measure the baseline before the page is tabled.
Two rules the columns enforce. An objective with no measure, baseline and target is a statement of intent, and belongs off the page. And an objective owned by a role that does not control the resource will not be delivered, whoever signs it.
Constraints are not objectives. A certification cycle or a regulatory application date says when something must already be true. Put it on the Constraints sheet, name what must be true by then, and check that an initiative reaches it before the date.
Status and other closed-option cells are numbered lists. Pick a listed value and do not invent a further one.
What this file does not contain. No personal data, no organisation names and no macros. The example rows are invented and describe no real organisation, objective or decision. This is method material published by an independent publication. It is not legal advice.
Template page: https://grcide.com/templates/one-page-security-strategy
Companion playbook: https://grcide.com/playbooks/security-strategy-on-one-page

## Strategy
ID | Business objective | Security objective (end condition) | Risk it moves (ID) | Measure | Baseline | Target | Target date | Owner (role) | Initiatives (IDs)
O-001 | EXAMPLE - delete. Sell into regulated customers without a security exception on every contract. | EXAMPLE - delete. Every production system authenticates through the central identity service, with no local administrative accounts. | R-001 | Production systems on central identity, as a share of the inventory | 62 per cent | 100 per cent | 2028-06-30 | Head of platform engineering | IN-01
O-002 | EXAMPLE - delete. Keep the customer platform available through a supplier failure. | EXAMPLE - delete. Every service supporting a critical business function has a tested exit route and a recovery objective met in test. | R-002 | Critical services with an exit route tested in the last year | 1 of 6 | 6 of 6 | 2027-12-31 | Head of customer operations | IN-02
O-003 | EXAMPLE - delete. Put AI-assisted case handling into production without an ungoverned system. | EXAMPLE - delete. Every AI system in production is registered, has a named owner, and its operators have completed role-specific literacy training. | R-011 | Registered AI systems with a named owner and trained operators | 0 of 4 | 4 of 4 | 2027-06-30 | Head of data and AI | IN-03

## Initiatives
ID | Initiative | Objective | Risk ID | Start | End | Resource | Status
IN-01 | EXAMPLE - delete. Migrate the remaining production systems onto the central identity service and remove local administrative accounts. | O-001 | R-001 | 2026-10-01 | 2027-09-30 | Two engineers, part time | 2. Running
IN-02 | EXAMPLE - delete. Cost, document and test an exit route for the hosted identity service supporting customer sign-in. | O-002 | R-002 | 2027-01-15 | 2027-11-30 | One architect, external test | 1. Planned
IN-03 | EXAMPLE - delete. Stand up the AI system register and the role-specific literacy sessions for operators. | O-003 | R-011 | 2026-11-01 | 2027-04-30 | Unfunded; one analyst requested | 1. Planned

## Constraints
Obligation | Instrument | Date | What must be true by then | Owner (role)
EXAMPLE - delete. Recertification audit of the management system. | Certification cycle | 2027-05-18 | Objectives, measures and review records available for three consecutive periods. | Head of compliance
EXAMPLE - delete. Risk-management measures in place for an in-scope entity. | Directive (EU) 2022/2555, Art. 21 | 2026-12-31 | Measures documented, approved by the management body, and evidenced against each point. | Head of compliance
EXAMPLE - delete. Registration and oversight of AI systems used in case handling. | Regulation (EU) 2024/1689 | 2027-06-30 | Register complete, owners named, and literacy measures delivered per role. | Head of data and AI

## Review log
Date | Event | Version | Body (role) | Outcome | Next review
2026-09-14 | EXAMPLE - delete. Strategy tabled for approval with the trade-off statement visible. | 1.0 | Executive committee | Approved. Objective O-003 recorded as unfunded, to be revisited at the next budget round. | 2027-09-13
2027-03-08 | EXAMPLE - delete. Half-year read of measures against targets. | 1.0 | Security forum | O-001 ahead of plan; O-002 behind, with the exit-route test moved to the third quarter. | 2027-09-13
2027-09-13 | EXAMPLE - delete. Annual re-read against the risk picture and the obligations register. | 1.1 | Executive committee | Objectives unchanged. One constraint added, and the baseline for O-002 restated. | 2028-09-11