## Read first
Risk acceptance record
Version 1.0, 2026-09-05. Licence CC BY 4.0, reuse and adapt with attribution to GRCIDE.
Template page: https://grcide.com/templates/risk-acceptance-record
Companion playbook: https://grcide.com/playbooks/risk-acceptance-and-residual-risk
Three sheets, one decision.
Acceptances holds one row per accepted risk. Authority table says who may accept each residual level, and for how long. Expiry log records what happened when an acceptance reached its date.
Before the first use
Delete every row marked EXAMPLE - delete. The example rows are invented and describe no real organisation, system or decision.
Fill the Authority table first, from the approved risk criteria. Nothing on the Acceptances sheet is valid until the approver's role matches a band in that table.
Closed columns
Against criteria takes 1. Within or 2. Above tolerance. Status takes 1. Active, 2. Expired or 3. Withdrawn. Decision at review takes 1. Re-accepted, 2. Lapsed to treatment or 3. Withdrawn.
Type the number and the word, exactly as printed. A free-text answer in a closed column breaks the expiry report.
Four rules the columns enforce
The residual level is recomputed after treatment. A level carried forward from before the controls existed is not a residual level.
The treatment considered and the reason it was declined are separate columns, because an assessor asks both questions.
Compensating controls are named as controls, each with an owner on the register. A sentence is not a measure.
Every row carries an expiry date and at least one event-based review trigger. An acceptance with no end is not a decision.
Standards this template follows
From ISO/IEC 27005:2022: risk owner at 3.1.5, residual risk at 3.1.17, risk acceptance at 3.2.8 and risk retention at 3.2.10. Also risk acceptance criteria at 6.4.2, approval by risk owners at 8.6.2, and acceptance of the residual information security risks at 8.6.3. Read from the publisher's preview (the 6.4.2, 8.6.2 and 8.6.3 references are clause titles from the contents listing).
From ISO 31000:2018: selection of risk treatment options at 6.5.2, treatment plans at 6.5.3, monitoring and review at 6.6, recording and reporting at 6.7. Clause numbers and titles were read from a licensed copy.
From ISO/IEC 27001:2022: risk assessment at 6.1.2, risk treatment at 6.1.3, roles and authorities at 5.3, control of documented information at 7.5.3. Titles read from the publisher's contents listing.
What this file does not contain
No personal data, no organisation names and no macros. This template is method material published by an independent publication. It is not legal advice and does not describe any specific organisation.
Standards and certification names are the property of their respective owners. GRCIDE is an independent publication and is not affiliated with, authorized, sponsored or endorsed by ISO, IEC, NIST or any other standards body.

## Acceptances
ID | Risk ID | Risk statement | Assessed level (before treatment) | Treatment considered | Reason declined | Residual level (after treatment) | Against criteria (1. Within / 2. Above tolerance) | Compensating controls (named, with owners) | Risk owner (role) | Approver (role, per the authority table) | Date accepted | Expiry | Review trigger (event) | Status (1. Active / 2. Expired / 3. Withdrawn)
A-001 | R-014 | EXAMPLE - delete. A public-facing reporting server runs an application version with a known remote-code-execution flaw and no supplier fix. | High | Upgrade to the supported release; migrate the workload to the managed platform. | The supported release drops an interface two downstream reports depend on. Migration is funded for the next financial year. | Medium | 1. Within | Traffic filter on the affected path (owner: network operations); service account restricted to read (owner: platform team); detection rule and daily queue review (owner: security operations) | Head of finance reporting | Head of finance reporting, countersigned by the security function | 2026-04-14 | 2027-04-14 | Supplier fix published; public exploit observed; migration date moves; exposure changes | 1. Active
A-002 | R-031 | EXAMPLE - delete. A legacy payroll interface transfers files without message-level integrity checking, so a tampered file would not be detected before processing. | High | Add signing at the interface; replace the interface with the supported API. | The supplier ends support for the interface in eighteen months, and the replacement is already scheduled inside that window. | High | 2. Above tolerance | Transfer restricted to one allow-listed host (owner: platform team); daily reconciliation of record counts and totals (owner: payroll operations) | Head of payroll operations | Executive committee, minuted | 2026-06-02 | 2026-12-02 | Replacement date slips; reconciliation exception raised; supplier withdraws support early | 1. Active
A-003 | R-007 | EXAMPLE - delete. A supplier holding personal data has no independent assurance report, and the contract predates the current security schedule. | Medium | Require an assurance report at renewal; move the service to an assured supplier. | Renewal falls in eleven months and the exit cost before then exceeds the assessed exposure by a wide margin. | Medium | 1. Within | Data set reduced to the fields the service needs (owner: data owner); quarterly evidence review against the security schedule (owner: procurement) | Data owner for employee records | Head of procurement, countersigned by the security function | 2025-11-18 | 2026-06-30 | Renewal opens; supplier incident reported; data set widens | 2. Expired

## Authority table
Residual level | Who may accept (role) | Who must be informed | Maximum duration
EXAMPLE - delete. Low | Risk owner | Risk function | 12 months
EXAMPLE - delete. Medium | Risk owner, countersigned by the security function | Management forum, at the next meeting | 12 months
EXAMPLE - delete. High | Named executive holding the accountable portfolio | Management forum, in session | 6 months
EXAMPLE - delete. Above tolerance | Not delegated. The governing body decides. | Governing body, in session, with the minute | 3 months

## Expiry log
Acceptance ID | Expiry date | Reviewed on | Decision at review (1. Re-accepted / 2. Lapsed to treatment / 3. Withdrawn) | Basis for the decision | New expiry | Decided by (role)
EXAMPLE - delete. A-003 | 2026-06-30 | 2026-06-16 | 2. Lapsed to treatment | Renewal opened on schedule, so the assurance report can be required in the new contract rather than accepted around. |  | Head of procurement
EXAMPLE - delete. A-007 | 2026-09-30 | 2026-09-16 | 1. Re-accepted | Exposure unchanged, compensating controls evidenced running for two quarters, decommissioning still funded for the following year. | 2027-03-30 | Named executive holding the accountable portfolio
EXAMPLE - delete. A-011 | 2026-08-31 | 2026-08-25 | 3. Withdrawn | The supplier fix was deployed in the August window, so the exposure the acceptance covered no longer exists. |  | Risk owner for the customer portal