## Register
ID | Risk statement (source / event / consequence) | Asset or objective | Likelihood (1-5, anchored) | Consequence (1-5, anchored) | Inherent level | Existing controls | Residual level | Treatment option (modify / retain / avoid / share) | Treatment plan | Control refs (Annex A) | Risk owner | Accepted by | Accepted on | Review date | Status
R-001 | EXAMPLE - delete. An external attacker using credentials bought from a broker signs in to the customer portal from an unmanaged device, and reads or exports personal data belonging to portal users. | Customer portal and the personal data it holds | 4 | 4 | High | Password policy; sign-in logging retained 90 days; quarterly access review | Medium | Modify | Enforce phishing-resistant multi-factor authentication for all portal sign-ins; alert on impossible-travel sign-ins | A.5.15, A.5.17, A.8.5, A.8.16 | Head of the customer-facing business line |  |  | 2026-12-01 | Treatment in progress
R-002 | EXAMPLE - delete. A single hosting region becomes unavailable for longer than the agreed recovery time, and the ordering service stops accepting orders for the duration of the outage. | Order-taking capability (revenue objective) | 2 | 4 | Medium | Daily backups tested twice a year; documented manual ordering fallback | Medium | Retain | No further treatment this cycle; retained against the stated acceptance criteria and re-tested at the next continuity exercise | A.5.29, A.5.30, A.8.13, A.8.14 | Chief operating role for service delivery | Executive accountable for the revenue objective | 2026-08-18 | 2027-02-18 | Accepted
R-003 | EXAMPLE - delete. An administrator with standing privileges makes an unreviewed change to a production access rule, and the change removes a control that the Statement of Applicability records as implemented. | Integrity of production access controls | 3 | 3 | Medium | Change record required; peer review documented for scheduled changes only | Medium | Modify | Move standing administrator rights to time-bound elevation; require a second approver for every production access-rule change | A.5.18, A.8.2, A.8.32 | Owner of the platform engineering function |  |  | 2026-11-15 | Treatment planned

## Scales
Anchored scales and decision criteria
Set these before the first workshop and keep them under version control. Descriptors below are a starting point, not a standard: replace every anchor with wording your own management forum will recognise and approve.
Likelihood (ISO/IEC 27005:2022, 6.4.3.3 and 7.3.3)
Value | Band | Anchored descriptor | Indicative frequency
1 | Rare | No occurrence known in this organisation or its sector; would need an unlikely combination of failures to happen at all. | Less often than once in ten years
2 | Unlikely | Plausible, but not observed here in the last three years; needs a specific opportunity that does not usually exist. | Once in three to ten years
3 | Possible | Has happened here at least once in the last three years, or is routinely reported in the sector. | Once in one to three years
4 | Likely | Happens in most years; the conditions are present and only partly controlled. | About once a year
5 | Almost certain | Happens several times a year, or is happening now and has not been stopped. | Monthly or more often
Consequence (ISO/IEC 27005:2022, 6.4.3.2 and 7.3.2)
Value | Band | Information anchor | Regulatory and financial anchor | Operational anchor
1 | Negligible | No reportable breach; no loss of a record that cannot be rebuilt from another source. | No regulatory duty triggered; cost absorbed inside normal operating budget. | Recovered inside the working day by the team that owns the service.
2 | Minor | Limited exposure of internal information; a small number of records affected and recoverable. | No notification duty; cost visible in a single cost centre for one period. | One service degraded for less than its agreed recovery time.
3 | Moderate | Confirmed exposure of personal or contractual data; correction needed in a system of record. | Notification duty likely; contractual service credits or a customer escalation. | One service unavailable beyond its agreed recovery time; manual fallback used.
4 | Major | Large-scale exposure of personal or commercially sensitive data; integrity of a system of record in question. | Notification duty certain; supervisory correspondence; material unbudgeted cost. | Several services unavailable for more than a day; customers publicly affected.
5 | Severe | Exposure or loss that the organisation cannot correct; special-category or safety-relevant data involved. | Enforcement action or loss of an authorisation the organisation needs to trade. | Loss of a capability the organisation exists to provide, for more than a week.
A band means nothing until all three anchors agree. Where they disagree, the highest anchor sets the value and the reason goes in the register row.
Level of risk (ISO/IEC 27005:2022, 6.4.3.4 and 7.3.4)
Published lookup, not a product of the two values. Ordinal scores are ranks, so multiplying them asserts arithmetic the scale does not carry. Read consequence down the left, likelihood across the top.
Consequence \ Likelihood | 1 | 2 | 3 | 4 | 5
5 | High | High | Critical | Critical | Critical
4 | Medium | High | High | Critical | Critical
3 | Low | Medium | Medium | High | High
2 | Low | Low | Medium | Medium | High
1 | Low | Low | Low | Low | Medium
Tie-break: where consequence is 5, the level never falls below High whatever the likelihood. Anything landing on High or Critical carries a semi-quantitative estimate as well, stated as a loss range and a frequency range.
Treatment options (ISO/IEC 27005:2022, 8.2)
Option | What it means | What the row must then carry
Modify | Change the likelihood, the consequence, or both, by adding or strengthening controls, or by removing the risk source. | A treatment plan with an owner and a date, and control references in the Statement of Applicability.
Retain | Take the risk knowingly at its current level, against the stated acceptance criteria. | A named acceptor, an acceptance date and an expiry or review date.
Avoid | Do not start, or stop, the activity that gives rise to the risk. | A decision record naming what was stopped and who agreed to stop it.
Share | Distribute the risk with another party by contract, by insurance, or by moving the activity to a provider. | The clause or policy that carries the share, and the residual level that stays.
Risk acceptance criteria (ISO/IEC 27005:2022, 6.4.2) - approved by management
Level | Who may accept | Maximum acceptance period | Record required | Condition
Low | Risk owner | 12 months | Register row only: acceptor, date, review date | No further treatment required while the level holds.
Medium | Risk owner, countersigned by the management-system owner | 12 months | Register row plus a note saying why treatment was not chosen | Re-assess if the asset, the threat picture or the scale anchors change.
High | The executive accountable for the affected objective | 6 months | Register row plus a minuted decision in the management forum | A treatment option must be costed and rejected on the record before retention.
Critical | Top management, in the management forum | 3 months | Minuted decision naming the acceptor, the expiry date and the trigger to revisit | Semi-quantitative estimate required before the decision is taken.
Delegation limits are an example only. Management sets them; the register applies them.

## Read first
Risk register template
Version 1.0, 2026-09-03
Licence: CC BY 4.0 - reuse and adapt with attribution to GRCIDE.
Template page: https://grcide.com/templates/risk-register
Companion playbook: https://grcide.com/playbooks/risk-register-people-trust
Before the first workshop
1. Fill in the Scales sheet first. A register scored against unwritten scales cannot be defended and cannot be compared across teams.
2. Have management approve the risk acceptance criteria on the Scales sheet. Setting them is a management act, not a facilitation act.
3. Delete the three example rows on the Register sheet. They exist to show the shape of a row and nothing else.
Two decisions are mandatory on every row
A. Treatment option. Exactly one of modify, retain, avoid or share. A blank cell is an unmade decision, and an unmade decision is a finding.
B. Acceptance. Whoever accepts the residual level is named in Accepted by, with the date in Accepted on. Both cells are filled, or neither is.
Standards this template follows
ISO/IEC 27005:2022 - risk criteria 6.4; identifying and describing risks 7.2.1; risk owners 7.2.2; consequence 7.3.2; likelihood 7.3.3; level of risk 7.3.4; evaluation 7.4; treatment options 8.2; controls and the Statement of Applicability 8.3 to 8.5; treatment plan, approval and acceptance 8.6.1 to 8.6.3.
ISO/IEC 27001:2022 - information security risk assessment 6.1.2 and 8.2; information security risk treatment 6.1.3 and 8.3; Annex A, information security controls reference.
ISO 31000:2018 - defining risk criteria 6.3.4; risk assessment 6.4; risk treatment 6.5; monitoring and review 6.6; recording and reporting 6.7.
Clause titles were read from the ISO Online Browsing Platform previews on 2026-09-03.
What this file does not contain
No personal data, no organisation names, no macros and no external links other than the two grcide.com pages above. The example rows are invented to show the format and describe no real event.
This template is method material published by an independent publication. It is not legal advice and does not describe any specific organisation.